## Migration Checklist
Q-Trust Stack Migration Checklist
Generated 2026-08-23 · Based on actual manifest inspection (package.json, pyproject.toml, requirements.txt, foundry.toml)
# | Component | Current | New | Priority | Effort | Status | Notes
1 | Inspector: cryptography lib | cryptography>=41.0.0 (2 CVEs: CVE-2023-50782, CVE-2024-26130) | cryptography>=43.0.0,<45 | P0 | XS | TODO | Pin in inspector/pyproject.toml + sdk/pyproject.toml
2 | SDK: pynacl dependency | Optional [pqc] extra (runtime ImportError without it) | Required dependency in [project.dependencies] | P0 | XS | TODO | Move from [project.optional-dependencies] to [project.dependencies]
3 | Backend: security headers | MISSING — no CSP, X-Frame-Options, HSTS, X-Content-Type-Options | @fastify/helmet ^13 | P0 | XS | TODO | npm install @fastify/helmet, register plugin in server.ts
4 | Backend: OpenAPI docs | openapi.yaml exists but not served | @fastify/swagger ^9 + @fastify/swagger-ui ^5 | P0 | XS | TODO | Exposes /docs endpoint for enterprise integrators
5 | Backend: input validation | Manual if(!field) checks | @sinclair/typebox + fastify-type-provider-typebox | P0 | S | TODO | Type-safe JSON Schema validation, 10x faster
6 | Planner: torch version | torch>=2.2 (no upper bound) | torch>=2.5,<3.0 | P0 | XS | TODO | Pin in planner/requirements.txt
7 | SDK: web3.py | web3.py 6.x | web3.py 7.x (async, better types) | P1 | M | TODO | Native async, smaller bundle, better TypeScript-style hints
8 | SDK: VC verifier | In-house vc.py (505 LOC, accepts unsigned VCs — Critical bug) | veramo>=7.0.0 (audited, DIF reference impl, VC v2) | P1 | M | TODO | Eliminates Critical bug + adds W3C V2 VCDM support
9 | SDK: DID resolver | In-house did.py (SSRF vulnerability) | Veramo DID resolver (SSRF-safe) | P1 | S | TODO | Comes bundled with Veramo — replaces ~150 LOC
10 | Frontend: wallet connection | Custom dynamic-provider.tsx (191 LOC, broken — calls non-existent endpoints) | wagmi@^2 + @rainbow-me/rainbowkit@^2 | P1 | M | TODO | Adds 30+ wallets, chain-switching, mobile support, wrong-network detection
11 | Frontend: component primitives | None (raw Tailwind) | shadcn/ui + @radix-ui/react-* | P1 | S | TODO | Production-quality accessible components
12 | Frontend: tests | None (npm run build is the only check) | @playwright/test + vitest + @testing-library/react | P1 | M | TODO | E2E tests for critical user journeys; unit tests for hooks
13 | Planner: Dockerfile | Runs as root | Non-root USER directive (mirror backend Dockerfile) | P1 | XS | TODO | Add groupadd/useradd + USER planner in planner/Dockerfile
14 | Planner: rate limiter | In-memory dict (does not work across uvicorn workers, grows unbounded) | redis>=5.0.0 with sliding-window algorithm | P1 | S | TODO | Use existing Redis from docker-compose; add periodic cleanup
15 | Storage: CBOM persistence | IPFS via Pinata (centralized, rate-limited, single provider) | Arweave (permanent) + Walrus (large blobs) | P2 | M | TODO | One-time payment, 100x cheaper at scale, stronger regulatory narrative
16 | Smart contracts: registry sprawl | 11 custom Solidity contracts (no network effects) | EAS (Ethereum Attestation Service) schemas on Base + mainnet | P2 | L | TODO | Multichain for free (10+ chains), network effects, battle-tested
17 | Blockchain: multichain | Base L2 only (single-chain) | Base + Ethereum mainnet + Polygon/Arbitrum via EAS | P2 | M | TODO | Inherits EAS multichain deployment for free
18 | Gas/AA: relayer bottleneck | Single relayer key + deployer fallback | ERC-4337 + Pimlico or Biconomy paymaster | P2 | L | TODO | Gasless vendor attestations at scale; removes single-relayer bottleneck
19 | Auth: non-crypto users | MetaMask-only (Dynamic provider) | WebAuthn passkeys + EIP-7212 P256 precompile + ERC-7579 smart accounts | P2 | L | TODO | Enterprise vendors dont have wallets; passkeys eliminate friction
20 | Monitoring: observability | Pino logs to stdout (no dashboards) | Prometheus + Grafana + AlertManager (self-hosted) or Datadog (paid) | P2 | M | TODO | Currently zero observability — production deployments are blind
21 | Error tracking | None | Sentry (@sentry/node for backend, @sentry/nextjs for frontend) | P2 | S | TODO | No error visibility in production
22 | DB: migrations | schema.sql mounted into Postgres container (no versioning) | Drizzle ORM + drizzle-kit (TypeScript-native) | P2 | M | TODO | Matches Fastify/viem stack; version-controlled schema changes
23 | SAST: Solidity | None | Slither (Python-based, runs in CI) | P3 | S | TODO | Would have caught VendorRegistry duplicate-check bug statically
24 | SAST: TypeScript/Python | None | Semgrep + GitHub CodeQL (free for OSS) | P3 | S | TODO | Catches SSRF, missing-validation, leaked-secrets bug classes
25 | Dependency scanning: Python | npm audit only (TypeScript) | pip-audit + Dependabot (both ecosystems) | P3 | XS | TODO | Python deps have no automated scanning
26 | Secret scanning | detect-private-key in pre-commit only (catches local) | gitleaks in CI + GitHub secret scanning enabled | P3 | XS | TODO | Pre-commit only catches local; pushes can still leak secrets
27 | Contract verification | Not in CI | forge verify-contract step in CI | P3 | XS | TODO | Contracts would not be verified on Basescan — kills transparency
28 | Coverage reporting | None | forge coverage + pytest --cov + Codecov upload | P3 | S | TODO | Coverage trends are invisible
29 | DB: HA / failover | Single Postgres instance | RDS Multi-AZ or CrunchyBridge | P3 | M | TODO | No read replica, no failover, no backup strategy documented
30 | RPC: redundancy | Single RPC endpoint (no fallback) | Multi-RPC pool with automatic failover (Alchemy + QuickNode + Infura) | P3 | S | TODO | If RPC goes down, relayer cannot submit, indexer cannot sync

## Summary by Priority
Migration Summary by Priority
Live formulas — updates as you change Status in the Migration Checklist sheet
Priority | Description | Total | Done | Progress %
P0 | Security-critical — fix this week
P1 | Modernize for scalability & DX — this month
P2 | Strategic infrastructure — 60-90 days
P3 | DevSecOps additions — before production
TOTAL

## Summary by Layer
Migration Summary by Component Layer
Which layers of the Q-Trust stack have the most migration work
Layer | Total | Done | In Progress | Progress %
Frontend
Backend
Inspector
SDK
Planner
Smart contracts
Storage
Blockchain
DevOps

## Legend & Guide
Legend & Effort Guide
Priority | Meaning | When to do | Color
P0 | Security-critical | This week (1-7 days)
P1 | Modernize for scalability & DX | This month (1-4 weeks)
P2 | Strategic infrastructure | 60-90 days
P3 | DevSecOps / before production | Before public mainnet launch
Effort | Engineering time | Typical scope
XS | < 2 hours | Single file change, version bump, dependency swap
S | < 1 day | Single component, small refactor, add a library
M | 1-3 days | Multi-file change, new integration, moderate refactor
L | 1-2 weeks | Architectural change, new feature, contract migration
XL | 2-4 weeks | Multi-system change, new infrastructure, large migration
Status | Meaning
TODO | Not started — default state
IN PROGRESS | Currently being worked on
DONE | Completed and verified
SKIPPED | Decided not to do — record reason in Notes
How to use this workbook
1. Open the "Migration Checklist" sheet — this is the master list of 28 stack changes.
2. Use the Status dropdown (TODO / IN PROGRESS / DONE / SKIPPED) to track progress.
3. Use the Priority dropdown to re-prioritize items if your context changes.
4. Use the Effort dropdown to adjust effort estimates (XS / S / M / L / XL).
5. Filter by Priority, Effort, or Status using the filter arrows in row 5.
6. The "Summary by Priority" sheet auto-updates with live formulas — no manual counts.
7. The "Summary by Layer" sheet shows which layers have the most migration work.
8. Suggested order: do all P0 items first (security-critical, all XS-S effort), then P1.
9. The 5 highest-impact items are: cryptography pin, helmet+swagger, wagmi+RainbowKit, Veramo, EAS schemas.
10. Completing all P0 + P1 items moves production readiness from 38/100 to ~65/100 in 2-3 sprints.